## MIO-SMIO
System Test - Pulse App
Defect Report
Application Name: HPL Pulse Application Version: V2.1.5 & V2.2.0 Legacy ID: 01014 Device: Realme 8 Android Version: 12
Tester Name: Jakia Rahman Role: Intern - MIS
Defect ID | Module / Feature | Test Case ID | Description of Issue | Steps to Reproduce | Expected Result | Actual Result | Status | Severity | Priority | Remarks
DEF-001 | Authentication (Login & OTP) | TC-LOGIN-004 | Password change prompt not shown after logging in with auto-generated password | 1. Reset password via Forgot Password. 2. Login with auto-generated password. 3. Observe post-login behavior. | System must force user to change auto-generated password. | No prompt shown, user lands on dashboard directly. | Open | High | High | Security risk; Still failing in v2.2.0.
DEF-002 | Basic Data Download | TC-BDATA-001 | CMS data not downloaded while others downloaded successfully. | 1. Trigger "Download Basic Data". 2. Compare downloaded data categories. | All categories (including CMS) must download. | CMS missing in v2.1.5. | Fixed | Medium | High | Fixed in v2.2.0.
DEF-003 | Doctor Management (Filtering) | TC-DOC-011 | Filtering of active doctor list not fully functional. | 1. Navigate to Doctor List. 2. Apply "Active" filter. | Only active doctors of selected submarket should display. | Filter does not apply correctly. | Open | Medium | Medium | Still failing in v2.2.0.
DEF-004 | Chemist Management (Validation) | TC-CHEM-003 | License number field validation failed earlier for alphanumeric entries. | 1. Add chemist with license number containing letters + digits. | System should accept alphanumeric values. | Earlier rejected. | Fixed | Low | Medium | Requirement clarified: License may contain alphanumeric.
DEF-005 | Chemist Management (Dropdown/Text Input) | TC-CHEM-004 | District dropdown could not reopen after selection. | 1. Add chemist. 2. Select district. 3. Try reopening dropdown. | User should reopen and change district. | Dropdown blocked after first selection. | Fixed | Low | Low | Clarified: Field allows dropdown and manual text input.
DEF-006 | Chemist Management (Dropdown/Text Input) | TC-CHEM-005 | Thana dropdown could not reopen after selection. | 1. Add chemist. 2. Select thana. 3. Try reopening dropdown. | User should reopen and change thana. | Dropdown blocked after first selection. | Fixed | Low | Low | Clarified: Field allows dropdown and manual text input.
DEF-007 | Chemist Management (Dropdown/Text Input) |  | District/Thana fields allow both dropdown selection and manual text input. | 1. Add chemist. 2. Select thana. 3. Try reopening dropdown. | User should reopen and change thana while keyboard open. | Dropdown blocked after first selection. | Fixed | Low | Low | Clarified: Field allows dropdown and manual text input.
DEF-008 | Geofence Management (Approval) | TC-GEO-009 | User unable to edit geofence before approval. | 1. Create geofence. 2. Attempt editing before manager approval. | Edit must be possible before approval. | Edit blocked. | Open | Medium | Medium | Still failing in v2.2.0.
DEF-009 | Geofence Management (Pending List) | TC-GEO-016 | Submitted doctors/chemists not visible in pending list. | 1. Create geofence with doctors/chemists. 2. Submit for approval. 3. Check pending list. | Submitted doctors/chemists must be visible. | Missing in pending list (v2.1.5). | Fixed | Medium | Medium | Fixed in v2.2.0.
DEF-010 | Geofence Management (Trigger) | TC-GEO-017 | Geofence triggers incorrectly without proper check-in/out. | 1. Delay check-in or skip check-out before 12 PM. 2. Observe trigger. | Geofence must trigger only after proper check-in/out. | Trigger occurs incorrectly. | Open | High | High | Still failing in v2.2.0; Major functional gap.
DEF-011 | Geofence Management (UI Indication) | TC-GEO-018 | Geofence indication missing in submarket list. | 1. Create geofence. 2. Open submarket list. | Submarket list should show geofence indication. | Indication missing. | Fixed | Low | Medium | Fixed in v2.2.0.
DEF-012 | Tour Plan (Leave Plan) | TC-TOUR-008 | Leave plan submission did not update session/location. | 1. Submit leave plan. 2. Verify session/location data. | Session/location must auto-update. | Did not update (v2.1.5). | Fixed | Medium | Medium | Fixed in v2.2.0.
DEF-013 | Tour Plan (Monthly Listing) | TC-TOUR-009 | Tour plan shown under wrong month in list. | 1. Create plan in September. 2. Open monthly tour plan list. | Plan should display under correct month (September). | Displays under October. | Open | Medium | Medium | Still failing in v2.2.0.
DEF-014 | Notifications (Navigation) | TC-NOTI-002 | Notifications list sometimes empty on click. | 1. Receive notification. 2. Tap notification. | Notification list should open with details. | Sometimes empty (non real-time). | Fixed | Low | Medium | Clarified: List refreshes only after sync/refresh.
DEF-015 | Notifications (Timing) | TC-NOTI-003 | Incorrect timing for check-out notifications. | 1. Skip or delay check-in/out. 2. Observe check-out notification. | Notification must show correct timing. | Shows wrong timing if user missed check-in/out. | Fixed | Low | Medium | Clarified: Depends on user behavior, not system bug.