## AM-RM
System Test – Pulse App
Test Case Execution Document
Test Run Information:
|  |  | Tester Name: Jakia Rahman Date of Test: 27 - 08 - 2025 | Application Name : Pulse App Application Version: V2.1.5 & V2.2.0 Account Role: AM/RM Legacy ID: 01002 Device: Samsung Galaxy M11 Android Version: 12
Test Execution Summary: | Result:
Total Test Scenarios Executed: | 10
Total Test Cases Executed: | 51
Passed: | 48
Failed: | 3
Test Scenario ID: TS-AM-001
Feature: Authentication
Sub-Feature: Login / Logout / Authentication with OTP
Scope: Covers positive login, negative login attempts, logout, and session handling.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-LOGIN-001 | Verify login with valid Legacy ID, OTP, and Password | Legacy ID - 01014 OTP - Auto Password - ********* | App installed, valid user account | 1. Enter valid Legacy ID 2. OTP auto-verified 3. Enter valid password | User successfully logs in and lands on Dashboard | Succesfully logged in into the app. | High | Pass | Pass | -
TC-LOGIN-002 | Verify login fails with invalid or blank credentials (Legacy ID / OTP / Password) | Invalid Legacy ID: 99999 Blank Legacy ID: -- Invalid Password: 123 Blank Password: -- | App installed | 1. Enter invalid Legacy ID → Verify error 2. Enter blank Legacy ID → Verify error 3. Enter invalid password → Verify error 4. Enter blank password → Verify error | System shows error messages and prevents login | 1. Invalid Legacy ID -> Shows "Invalid User ID" 2. Blank Legacy ID -> Shows "Enter Employee ID" 3. Invalid Password -> Shows "Invalid login attempt" 4. Blank Password -> Shows "Enter Password" | High | Pass | Pass | -
TC-LOGIN-003 | Verify "Forgot Password" functionality | Legacy ID: 01014 Registered Phone: +88017xxxxxxx | User registered with valid phone number | 1. Tap “Forgot Password” 2. Auto-password sent to user’s registered phone 3. Login with auto-password | User logs in successfully with auto-password | Login Successful with Auto-sent Password. | High | Pass | Pass | -
TC-LOGIN-004 | Verify password change prompt after logging in with auto-password (Regression Check) | Legacy ID: 01014 Auto Password: XYz1234 | Logged in using auto-password | 1. Login using auto-password 2. Check system behavior | System should prompt user to set a new password immediately | Set New Password prompt not showing in new version. | Medium | Fail | Fail | System must ensure user to change auto-generated password.
TC-LOGIN-005 | Verify session logout and re-login | Legacy ID: 01014 Password: Abc@1234 | Logged in user | 1. Logout from the app 2. Login again with valid credentials | User is logged out successfully and can re-login | Re-login successful with valid password. | High | Pass | Pass | -
TC-LOGIN-006 | Verify multi-device restriction (if applicable) | Device A: Realme 8 Device B: Samsung Galaxy M11 Legacy ID: 01014 Authenticate | User logged in on Device A | 1. Login with Device A (valid credentials) 2. Try to login with Device B using same Legacy ID | Verify restriction: multiple devices cannot login with same Legacy ID | 1. Shows Warning "Another device logged in with the same Legacy ID" 2. OTP is sent to the other device but automatic authentication can't be done. | High | Pass | Pass | -
Test Scenario ID: TS-AM-002
Feature: Basic Data Download
Sub-Feature: All Basic Data
Scope: Ensures that the application downloads all required datasets for offline use and handles different internet conditions correctly.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-BDATA-001 | Verify all basic data downloads successfully | Internet: Stable connection | User logged in, valid credentials | 1. Navigate to Basic Data Download module 2. Click Download Basic Data 3. Verify each data is downloaded | All datasets download successfully and are available offline | CMS Data not downloaded while others are downloaded successfully | High | Fail | Pass | -
TC-BDATA-002 | Verify behavior when internet connection is OFF during download | Internet OFF | User logged in | 1. Navigate to Basic Data Download 2. Turn off internet 3. Try Download Basic Data | System shows error “No Internet Connection” and prevents download | Error message shown, no data downloaded | High | Pass | Pass | -
TC-BDATA-003 | Verify retry option after failed download | Internet: Intermittent connection | User logged in | 1. Start Basic Data Download 2. Interrupt connection midway 3. Resume internet and retry | System retries download from where it left off or restarts cleanly | Partial data downloaded, retry worked |  | Pass | Pass | -
Test Scenario ID: TS-AM-003
Feature: Notifications
Sub-Feature: Alerts & Background
Scope: Verify in-app notifications for approval requests, system alerts, and MIO/SMIO activities are triggered and displayed correctly, including background notifications.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-NOT-001 | Verify AM/RM receives notification for pending doctor approval requests | Pending doctor requests exist | AM/RM logged in, notifications allowed | 1. Trigger pending doctor request 2. Wait for notification | Notification appears in-app and in background with correct details | Notification received successfully for pending doctor requests | High | Pass | Pass | -
TC-NOT-002 | Verify AM/RM receives notification for pending chemist approval requests | Pending chemist requests exist | Same as above | 1. Trigger system alert 2. Check in-app and background notifications | Notification appears correctly | Notification received successfully for chemist requests | High | Pass | Pass | -
TC-NOT-003 | Verify system alert notifications are received | System alerts triggered (e.g., server maintenance, updates) | AM/RM logged in, notifications allowed | 1. Trigger system alert 2. Check in-app and background notifications | System alert displayed correctly | System alert received successfully | High | Pass | Pass | -
TC-NOT-004 | Verify notifications for MIO/SMIO activity (check-in/out, geofence) | Activity logs generated | Same as above | 1. MIO/SMIO performs activity 2. Check notification | Activity notification displayed with correct details | Activity notification received successfully | High | Pass | Pass | -
TC-NOT-005 | Verify notifications appear when app is running in background | Same as above | AM/RM logged in, app minimized | 1. Minimize app 2. Trigger any notification (approval/activity/alert) 3. Check notification | Notifications appear correctly even in background | Notifications appeared correctly in background | High | Pass | Pass | -
TC-NOT-006 | Verify device settings allow notifications | Device settings toggled | Device notifications enabled | 1. Disable notifications in device settings 2. Trigger any alert 3. Check notification | Notification should not appear; system handles it gracefully | Notification blocked as expected when device settings disabled | High | Pass | Pass | -
Test Scenario ID: TS-AM-004
Feature: Submarket Management
Sub-Feature: Create / Active / Inactive
Scope: Verify AM/RM can create submarkets by filling required fields (Market, Location, Name, Description, Address), activate/inactivate existing submarkets, prevent duplicates, and ensure inactive submarkets are not selectable by MIO/SMIO.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Previous Version (v2.1.5) | Remarks
TC-SUB-001 | Verify AM/RM can create a new submarket with valid details | Market: “Mohonganj-1” Location: “Mohonganj” Name: “Test” Description: “Test” Address: “test” | AM/RM logged in with Submarket Management access | 1. Log in as AM/RM 2. Navigate to Submarket 3. Click “Create Submarket + icon” 4. Select Market, enter Location, Name, Description, Address 5. Save | Submarket is created successfully and displayed in list | Submarket “Test” created successfully and listed under selected market. | High | Pass | Pass | -
TC-SUB-002 | Verify system prevents duplicate submarket creation | Market: “Mohonganj-1” Location: “Mohonganj” Name: “Test” Description: “Test” Address: “test” | A submarket with same Market + Location + Name already exists | 1. Log in as AM/RM 2. Try to create a new submarket with same details 3. Save | Duplicate submarket can be created | Duplicate submarket can be created | High | Pass | Pass | -
TC-SUB-003 | Verify mandatory fields validation during submarket creation | Leave Market blank / Leave Name blank | AM/RM logged in | 1. Log in as AM/RM 2. Navigate to Create Submarket 3. Leave Market or Name empty 4. Save | System shows validation error “Market and Name are required fields” | Validation error displayed: “Market is required” / “Name is required” | High | Pass | Pass | -
TC-SUB-004 | Verify AM/RM can activate an inactive submarket | Existing inactive submarket | AM/RM logged in | 1. Log in as AM/RM 2. Go to Submarket list 3. Choose an inactive submarket 4. Click “Activate” | Submarket status changes to Active and is selectable by MIO/SMIO | Submarket activated successfully and visible to MIO/SMIO | High | Pass | Pass | -
TC-SUB-005 | Verify AM/RM can inactivate an active submarket | Existing active submarket | AM/RM logged in | 1. Log in as AM/RM 2. Go to Submarket list 3. Choose an active submarket 4. Click “Inactivate” | 1. Submarket status changes to Inactive (without any active doctor/chemist) and is not selectable by MIO/SMIO 2. Submarkets with active doctors/chemists can't be inactive. | 1. Submarket (without any active doctor/chemist) inactivated successfully and hidden from MIO/SMIO 2. Submarkets with active doctors/chemists can't get inactive. | High | Pass | Pass | -
TC-SUB-006 | Verify inactive submarkets are not available for MIO/SMIO selection | Inactive submarket exists | MIO/SMIO logged in | 1. Log in as MIO/SMIO 2. Navigate to Submarket selection dropdown 3. Review list | Inactive submarket does not appear in Submarket List | Inactive submarket not displayed in MIO/SMIO Submarket List | High | Pass | Pass | -
Test Scenario ID: TS-AM-005
Feature: Doctor Management
Sub-Feature: Pending Requests
Scope: Verify AM/RM can approve or reject pending doctor requests (including doctor transfer requests), ensure approved doctors move to the active list, rejected requests are logged with reasons, and duplicates are prevented.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-DOC-001 | Verify AM/RM can view pending doctor requests | List of pending doctor requests | AM/RM logged in with doctor approval rights, pending requests exist | 1. Log in as AM/RM 2. Navigate to Notification → Pending Requests | Pending doctor requests are displayed | Pending doctor requests shown correctly | High | Pass | Pass | -
TC-DOC-002 | Verify AM/RM can approve a pending doctor request | Doctor Request ID: DR-101 | Same as above | 1. Select a pending doctor request 2. Click “Approve” 3. Confirm action | Doctor request approved and doctor moves to Active list | Doctor DR-ARIFA approved and added to Active list | High | Pass | Pass | -
TC-DOC-003 | Verify AM/RM can reject a pending doctor request | Doctor Request ID: DR-102, Rejection Reason: “Incomplete details” | Same as above | 1. Select a pending doctor request 2. Click “Reject” 3. Enter rejection reason 4. Confirm action | Request rejected and logged with rejection reason | Doctor DR-MAMUN rejected with reason logged | High | Pass | Pass | -
TC-DOC-004 | Verify AM/RM can approve doctor transfer requests | Doctor Transfer Request: DR-103 → from Market A to Market B | Transfer request exists | 1. Select doctor transfer request 2. Click “Approve Transfer” 3. Confirm action | Doctor successfully transferred to new market and appears in updated active list | Doctor DR-ARIFA transferred from Sub-Market A → Sub-Market B successfully | High | Pass | Pass | -
TC-DOC-005 | Verify AM/RM can reject doctor transfer requests | Doctor Transfer Request: DR-104, Reason: “Duplicate entry” | Transfer request exists | 1. Select doctor transfer request 2. Click “Reject Transfer” 3. Enter rejection reason 4. Confirm action | Transfer request rejected and logged with reason | Doctor DR-ARIFA transfer request rejected, logged with reason | High | Pass | Pass | -
TC-DOC-006 | Verify system allows duplicate doctor approvals | Doctor Request already approved in system | Same as above | 1. Try to approve a doctor who is already active 2. Save action | System allows duplicate approval | System allows duplicate approval | High | Pass | Pass | -
Test Scenario ID: TS-AM-006
Feature: Chemist Management
Sub-Feature: Pending Requests
Scope: Verify AM/RM can approve or reject pending chemist requests; approved chemists move to the active list; rejected requests are logged with reasons; mandatory validations are checked before approval.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-CHEMIST-001 | Verify AM/RM can view pending chemist requests | List of pending chemist requests | AM/RM logged in, pending requests exist | 1. Log in as AM/RM 2. Navigate to Chemist Approval → Pending Requests | Pending chemist requests displayed | Pending chemist requests shown correctly | High | Pass | Pass | -
TC-CHEMIST-002 | Verify AM/RM can approve chemist request | Chemist Request | Same as above | 1. Select a pending chemist request 2. Click “Approve” 3. Confirm action | Chemist added to Active list | Chemist CH-201 approved successfully | High | Pass | Pass | -
TC-CHEMIST-003 | Verify AM/RM can reject chemist request | Chemist Request, Rejection Reason: “Incomplete address” | Same as above | 1. Select request 2. Click “Reject” 3. Enter reason 4. Confirm | Request rejected, logged with reason | Chemist CH-202 rejected with reason logged | High | Pass | Pass | -
TC-CHEMIST-004 | Verify mandatory validations before approval | Missing Name/License No. | Request missing required fields | 1. Try to approve a chemist with missing mandatory data 2. Save | System prevents approval, shows validation error | Validation error shown “Name/License required” | High | Pass | Pass | -
Test Scenario ID: TS-AM-007
Feature: Geofence Management
Sub-Feature: Pending Requests
Scope: Verify AM/RM can approve/reject geofence requests; once approved, MIO/SMIO cannot edit; geofence details must be checked on the map before approval.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-GF-001 | Verify AM/RM can view pending geofence requests | Pending geofence requests exist | AM/RM logged in, requests exist | 1. Log in as AM/RM 2. Navigate to Submarket → Geofence Points → Pending Requests | Pending requests displayed | Requests displayed correctly | High | Pass | Pass | -
TC-GF-002 | Verify AM/RM can select a submarket and view its geofence points | Geofence points exist for submarket | Same as above | 1. Select submarket 2. View list/map of geofence points | Geofence points displayed for selected submarket | Geofence points displayed correctly | High | Pass | Pass | -
TC-GF-003 | Verify AM/RM can set radius for geofence within allowed limits | Radius: 50m (valid) | Same as above | 1. Select geofence 2. Enter radius 50m 3. Click Approve | Geofence approved and moved to Active Geofence list | Geofence approved successfully | High | Pass | Pass | -
TC-GF-004 | Verify AM/RM cannot approve geofence if radius is outside allowed limits (below 20m or above 500m) | Radius: 10m / 600m | Same as above | 1. Select geofence 2. Enter radius 10m → Click Approve 3. Enter radius 600m → Click Approve | System shows error: “Radius must be between 20m and 500m” for both cases | Error displayed correctly for 10m & 600m | High | Pass | Pass | -
TC-GF-005 | Verify approved geofence moves to Active Geofence list | Approved geofence | Same as above | 1. Approve geofence with valid radius | Geofence appears in Active Geofence list | Geofence listed as active | High | Pass | Pass | -
TC-GF-006 | Verify AM/RM receives notification when a colleague enters approved geofence | Active geofence, colleague enters area | Same as above | 1. Colleague enters geofence 2. Check AM/RM notifications | Notification received for colleague entering geofence | Notification received successfully | High | Pass | Pass | -
TC-GF-007 | Verify AM/RM can reject geofence request with reason | Pending geofence request, Reason: “Incorrect location” | Same as above | 1. Select geofence 2. Click Deny 3. Enter reason 4. Confirm | Request rejected and logged with reason | Request rejected with reason logged | High | Pass | Pass | -
Test Scenario ID: TS-AM-008
Feature: Monitoring
Sub-Feature: MIO/SMIO Activity
Scope: Verify AM/RM can monitor MIO/SMIO check-in, check-out, and geofence history with accurate, real-time updates, including filters and date ranges.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-MONITOR-001 | Verify AM/RM can view MIO/SMIO activity history | Activity records | AM/RM logged in, activities exist | 1. Log in as AM/RM 2. Navigate to Attendance History | Activity list displayed | Activity displayed correctly | High | Pass | Pass | -
TC-MONITOR-002 | Verify check-in/check-out history displayed accurately | Attendance records | Same as above | 1. Select employee 2. View check-in/out history | Accurate records shown | Records correct | High | Pass | Pass | -
TC-MONITOR-003 | Verify geofence entry/exit history is displayed | Geofence logs | Same as above | 1. Select employee 2. View geofence history | Entry/exit logs shown correctly | Logs displayed correctly | High | Pass | Pass | -
TC-MONITOR-004 | Verify filters (date, employee, location) work in monitoring | Filters applied | Same as above | 1. Apply filters (by date/employee/location) 2. Review | Filtered results displayed correctly | Filters working correctly | High | Pass | Pass | -
Test Scenario ID: TS-AM-009
Feature: Tour Plan Approval
Sub-Feature: Submission Requests
Scope: Verify AM/RM can approve or reject tour plans submitted by MIO/SMIO; rejected ones return with remarks; prevent duplicate/invalid plans.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-TOUR-001 | Verify AM/RM can view pending tour plans | List of pending plans | AM/RM logged in, plans exist | 1. Log in as AM/RM 2. Navigate to Tour Plan Module → Select Date From Calender → Pending | Pending tour plans displayed | Plans displayed correctly | High | Pass | Pass | -
TC-TOUR-002 | Verify AM/RM can approve tour plan | Session: Morning, Location: HQ Miscellaneous: Meeting Submarkets: MOHANGANJ , LIPSHA | Same as above | 1. Select plan 2. Click “Approve” 3. Confirm | Plan approved and marked active | Plan approved | High | Pass | Pass | -
TC-TOUR-003 | Verify AM/RM can reject tour plan with remarks | Tour Plan , Remark: “Rejected” | Same as above | 1. Select plan 2. Click “Reject” 3. Enter reason 4. Confirm | Plan rejected with remark logged | Plan rejected with reason | High | Pass | Pass | -
TC-TOUR-004 | Verify supervisor can view both own and officer-wise tour plans | Supervisor account, officer plans exist | Same as above | 1. Login as Supervisor 2. Open Tour Plan module 3. Select from dropdown "Own" and "colleague A" 4. Observe displayed plans | Own plan and colleague’s plans are correctly displayed depending on selection | Own plan and colleague’s plans are correctly displayed depending on selection | High | Pass | Pass | -
TC-TOUR-005 | Verify plan list shows correct month after plan creation | Create Plan For September | User logged in as MIO/SMIO | 1. Create a plan for September 2. Check plan list | Plan should appear under September | Plan appears under October | High | Fail | Fail | Plan created in September shows under October in list

## MIO-SMIO
System Test – Pulse App
Test Case Execution Document
Test Run Information:
|  |  | Tester Name: Jakia Rahman Date of Test: 27 - 08 - 2025 | Application Name : Pulse App Application Version: V2.1.5 & V2.2.0 Account Role: MIO/SMIO Legacy ID: 01014 Device: Realme 8 Android Version: 12
Test Execution Summary: | Result
Total Test Scenarios Executed: | 10
Total Test Cases Executed: | 77
Passed: | 59
Failed: | 18
Test Scenario ID: TS-MIO-001
Feature: Authentication
Sub-Feature: Login / Logout / Authentication with OTP
Scope: Covers positive login, negative login attempts, logout, and session handling.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-LOGIN-001 | Verify login with valid Legacy ID, OTP, and Password | Legacy ID - 01014 OTP - Auto Password - ********* | App installed, valid user account | 1. Enter valid Legacy ID 2. OTP auto-verified 3. Enter valid password | User successfully logs in and lands on Dashboard | Succesfully logged in into the app. | High | Pass | Pass | -
TC-LOGIN-002 | Verify login fails with invalid or blank credentials (Legacy ID / OTP / Password) | Invalid Legacy ID: 99999 Blank Legacy ID: -- Invalid Password: 123 Blank Password: -- | App installed | 1. Enter invalid Legacy ID → Verify error 2. Enter blank Legacy ID → Verify error 3. Enter invalid password → Verify error 4. Enter blank password → Verify error | System shows error messages and prevents login | 1. Invalid Legacy ID -> Shows "Invalid User ID" 2. Blank Legacy ID -> Shows "Enter Employee ID" 3. Invalid Password -> Shows "Invalid login attempt" 4. Blank Password -> Shows "Enter Password" | High | Pass | Pass | -
TC-LOGIN-003 | Verify "Forgot Password" functionality | Legacy ID: 01014 Registered Phone: +88017xxxxxxx | User registered with valid phone number | 1. Tap “Forgot Password” 2. Auto-password sent to user’s registered phone 3. Login with auto-password | User logs in successfully with auto-password | Login Successful with Auto-sent Password. | High | Pass | Pass | -
TC-LOGIN-004 | Verify password change prompt after logging in with auto-password (Regression Check) | Legacy ID: 01014 Auto Password: XYz1234 | Logged in using auto-password | 1. Login using auto-password 2. Check system behavior | System should prompt user to set a new password immediately | Set New Password prompt not showing in new version. | Medium | Fail | Fail | System must ensure user to change auto-generated password.
TC-LOGIN-005 | Verify session logout and re-login | Legacy ID: 01014 Password: Abc@1234 | Logged in user | 1. Logout from the app 2. Login again with valid credentials | User is logged out successfully and can re-login | Re-login successful with valid password. | High | Pass | Pass | -
TC-LOGIN-006 | Verify multi-device restriction (if applicable) | Device A: Realme 8 Device B: Samsung Galaxy M11 Legacy ID: 01014 Authenticate | User logged in on Device A | 1. Login with Device A (valid credentials) 2. Try to login with Device B using same Legacy ID | Verify restriction: multiple devices cannot login with same Legacy ID | 1. Shows Warning "Another device logged in with the same Legacy ID" 2. OTP is sent to the other device but automatic authentication can't be done. | High | Pass | Pass | -
Test Scenario ID: TS-MIO-002
Feature: Basic Data Download
Sub-Feature: All Basic Data
Scope: Ensures that the application downloads all required datasets for offline use and handles different internet conditions correctly.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-BDATA-001 | Verify all basic data downloads successfully | Internet: Stable connection | User logged in, valid credentials | 1. Navigate to Basic Data Download module 2. Click Download Basic Data 3. Verify each data is downloaded | All datasets download successfully and are available offline | CMS Data not downloaded while others are downloaded successfully | High | Fail | Pass | -
TC-BDATA-002 | Verify behavior when internet connection is OFF during download | Internet OFF | User logged in | 1. Navigate to Basic Data Download 2. Turn off internet 3. Try Download Basic Data | System shows error “No Internet Connection” and prevents download | Error message shown, no data downloaded | High | Pass | Pass | -
TC-BDATA-003 | Verify retry option after failed download | Internet: Intermittent connection | User logged in | 1. Start Basic Data Download 2. Interrupt connection midway 3. Resume internet and retry | System retries download from where it left off or restarts cleanly | Partial data downloaded, retry worked | High | Pass | Pass | -
Test Scenario ID: TS-MIO-003
Feature: Doctor Management
Sub-Feature: Add / Edit / Transfer / Inactive / Group Doctors
Scope: Verify that MIO/SMIO users can create, edit, transfer, inactivate, and manage doctors correctly, including validations, pending list submissions, and active list filtering.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Previous Version (v2.1.5) | Remarks
TC-DOC-001 | Verify navigation to Doctor Management module | Respective Sub-Market already created | Logged in as MIO/SMIO | Tap Doctor Management | Screen opens with Options - Create, Show Active List, Show Pending List | Screen opens with all options | High | Pass | Pass | -
TC-DOC-002 | Add new Doctor with valid data | Name, Phone, Email, License, Market/Submarket, District, Thana, Image | Logged in as MIO/SMIO | Tap Create Doctor → Fill valid details → Submit | 1. Doctor Creation Form Opens 2. Shows Warning for Mandatory Fields 3. At Least 6 Targted Brands and 3 Other Brands must be chosen. 4. Sbmitted with All Valid Details 5. Goes to Pending list | New Doctors are added with all valid data | High | Pass | Pass | -
TC-DOC-003 | Mandatory field validation | 1. Leave Mandatory Fields blank 2. Fill with incorrect formate of Phone Number, Email, License Number | Logged in as MIO/SMIO | Fill incomplete form → Submit | Error messages shown, prevent submission | 1. Error Messages shown for every blank mandatory fileds. 2. Form Submits with incorrect email format 3. Form Submits without Phone Number / Correct Format | Medium | Pass | Pass | Field is optional; format validation not required
TC-DOC-004 | Edit existing Doctor | Change Name/Phone/License | Doctor exists | Select Doctor → Edit → Submit | 1. Doctor Name Can't be Updated 2. Updates go to Pending list or Draft successfully | 1. Doctor Name Can't be Updated 2. Updates go to Pending list or Draft successfully | Medium | Pass | Pass | -
TC-DOC-005 | Transfer Doctor to another Submarket | Select Doctor, choose Submarket | Doctor exists | Tap Transfer → Select Submarket → Submit | Doctor Transfers Correctly and shown on New Submarket List | Transfer is Successful and showing in the new Submarket list. | High | Pass | Pass | -
TC-DOC-006 | Inactive Doctor | Existing Doctor | Doctor exists | Select Doctor → Inactive → Confirm | 1. Inactive List goes to Supervisor for approval. | Shows list of inactive doctor for approval | High | Pass | Pass | -
TC-DOC-008 | Add new Group Doctor | Submarket, Institution, District, Thana, Ward, Number of non-coded doctors | Logged in as MIO/SMIO | Tap Create Group Doctor → Fill → Draft/Submit | Saved as Draft or submitted → Pending list | Shows list of doctor | High | Pass | Pass | -
TC-DOC-009 | Pending list check | Newly submitted Doctor/Inactive Doctor/ Group Doctor | Doctor submitted or edited/made inactive | Open Pending list | Submitted entries visible for supervisor approval | Shows List of - 1. Newly Added Doctors 2. Inactive Doctors | High | Pass | Pass | -
TC-DOC-010 | Duplicate Doctor entry | Doctor exists with same Phone/License | Logged in as MIO/SMIO | Create duplicate Doctor with Same Details→ Submit | Duplicate Doctors Created | Duplicate Doctors Created | Medium | Pass | Pass | -
TC-DOC-011 | Active Doctor List Shows All Doctors Together/ Sub- Market Wise Filtering | Active Doctor List of All Sub-Market | Logged in as MIO/SMIO | Open Active Doctors list → Refresh | 1. All doctors of MIO’s submarket appear 2. Clicking respective Submarket shows only their doctors 3. Refresh works correctly | 1. All doctors initially shown 2. Click another Submarket 3. correct filtered doctors shown 4. Refresh still shows all doctors again of all submarkets even though filter is applied | Medium | Fail | Fail | Refresh still shows all doctors again of all submarkets even though filter is applied
Test Scenario ID: TS-MIO-004
Feature: Chemist Management
Sub-Feature: Add / Edit / Dropdown / Validation
Scope: Verify that MIO/SMIO users can add new chemists, validate mandatory fields, select districts/thanas correctly, and interact with dropdowns properly.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-CHEM-001 | Verify adding a new Chemist with all valid inputs | Name: Maa Pharmacy Phone: 017xxxxxxxx Email: maa@gmail.com License: 123456 District: Dhaka Thana: Uttara Depo: Dhaka Depo Submarket: Uttara-1 Image: Uploaded | Logged in as MIO/SMIO | 1. Navigate to Chemist Module 2. Tap Create New Chemist 3. Enter all valid details 4. Save | Chemist should be created successfully and visible in the list | Chemist Added Successfully | High | Pass | Pass | -
TC-CHEM-002 | Verify mandatory field validation while adding Chemist | Leave Name / Phone / District blank | Logged in as MIO/SMIO | 1. Tap Create New Chemist 2. Leave required fields blank 3. Save | System should prevent save and show error messages (“Name required”, “Phone required”, etc.) | 1. Shown error message for mandatory fields - Name, Address, Phone Number, District, Thana,Submarket, Image . 2. No Error For Email, Drug License Number. | Medium | Pass | Pass | Field is optional; format validation not required
TC-CHEM-003 | Verify drug license field accepts only numbers | Enter input: ABC123, !@#, 45678 | Logged in as MIO/SMIO | 1. Tap Create New Chemist 2. Enter letters or special chars in License field 3. Save | System should allow only every input | System should allows every input format | Medium | Fail | Pass | Format validation not required
TC-CHEM-004 | Verify district dropdown selection works correctly | District: Dhaka | Logged in as MIO/SMIO | 1. Tap District dropdown 2. Select district 3. Try reopening dropdown to change selection | User should be able to select and re-select districts smoothly | Dropdown doesn’t reopen; shows spelling correction prompt | Medium | Fail | Pass | District/Thana fields allow both dropdown selection and manual text input.
TC-CHEM-005 | Verify thana dropdown selection works correctly | Thana: Uttara | Logged in as MIO/SMIO | 1. Tap Thana dropdown 2. Select thana 3. Try reopening dropdown to change selection | User should be able to re-select thana smoothly | Dropdown doesn’t reopen; shows spelling correction prompt | Medium | Fail | Pass | District/Thana fields allow both dropdown selection and manual text input.
TC-CHEM-006 | Verify district dropdown scrolls when keyboard open | District list long enough to scroll | Logged in as MIO/SMIO | 1. Tap District dropdown while keyboard is open 2. Scroll list | Dropdown list should scroll properly | Dropdown not scrollable when keyboard open | Medium | Fail | Pass | District/Thana fields allow both dropdown selection and manual text input.
Test Scenario ID: TS-MIO-005
Feature: Geofence Management
Sub-Feature: Create / Edit / Trigger / Record / Map View
Scope: Verify that MIO/SMIO users can create geofences with proper validation, submit for approval, trigger notifications correctly, and view records/maps. Also includes dropdown/scroll behavior and check-in dependencies.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-GEO-001 | Verify submitting Geofence without a name | Geofence Name = Blank | Logged in as MIO/SMIO | 1. Open Submarket module 2. Select Submarket 3. Click "Geofence Points of This Submarket" 4. Click on "+" Icon 2. Leave Geo-Fence Name blank 3. Select Chemist/Doctor 4. Tap Set Location | Error shown: “Please Enter Geofence Name”, Geofence not submitted | Error shown: “Please Enter Geofence Name | High | Pass | Pass | -
TC-GEO-002 | Verify submitting Geofence without selecting Doctor | Name = “Test Geo - Only Chemist” Chemist selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Select only Chemist 3. Tap Set Location | Geofence created successfully with Chemist only → Pending list | Geofence created successfully | High | Pass | Pass | -
TC-GEO-003 | Verify submitting Geofence without selecting Chemist | Name = “Test Geo - Only Doctor” Doctor selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Select only Doctor 3. Tap Set Location | Geofence created successfully with Doctor only → Pending list | Geofence created successfully | High | Pass | Pass | -
TC-GEO-004 | Verify submitting Geofence without selecting Doctor & Chemist | Name = “Test Geo” No Doctor/Chemist selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Leave Doctor/Chemist blank 3. Tap Set Location | Error shown: “Select at least one Doctor or Chemist” | Error shown: “Please Select at least one Doctor or Chemist” | High | Pass | Pass | -
TC-GEO-005 | Verify submitting Geofence with both Doctor & Chemist | Name = “Test Geo” Doctor + Chemist selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Select Doctor & Chemist 3. Tap Set Location | Geofence created successfully with both selected → Pending list | Geofence created successfully | High | Pass | Pass | -
TC-GEO-006 | Verify multiple Doctors selection | Name = “Test Geo” Doctors = 2+ selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Select multiple Doctors 3. Tap Set Location | Geofence created successfully with multiple Doctors | Geofence created successfully | High | Pass | Pass | -
TC-GEO-007 | Verify multiple Chemists selection | Name = “Test Geo” Chemists = 2+ selected | Logged in as MIO/SMIO | 1. Enter Geofence Name 2. Select multiple Chemists 3. Tap Set Location | Geofence created successfully with multiple Chemists | Geofence created successfully | High | Pass | Pass | -
TC-GEO-008 | Verify Pending → Approval workflow | Submitted Geofence | Geofence submitted and in Pending List | 1. Submit Geofence 2. Check Pending list 3. Supervisor approves | Geofence disappears from Pending list, moves to Active list | Shows on Active List after Supervisors Approval | High | Pass | Pass | -
TC-GEO-009 | Verify Edit option before supervisor approval | Pending Geofence | Geofence created and in Pending | 1. Open Pending Geofence 2. Edit details (Doctor, Chemist, Location) 3. Save | Changes updated successfully until Supervisor approval | No Edit Option Found on the Geofences of Pending List. | High | Fail | Fail | Not Fixed Yet
TC-GEO-010 | Verify Geofence can be edited after supervisor approval | Active Geofence | Supervisor approved Geofence | 1. Open Active Geofence 2. Try Edit | Edit option available on active Geofence | Edit option available on active Geofence | High | Pass | Pass | -
TC-GEO-011 | Verify Geofence triggers only after Check-In | Active Geofence, location mapped | MIO/SMIO inside Geofence radius | 1. Go near Geofence area 2. Without Check-In → verify 3. With Check-In → verify | Geofence triggers only after Check-In | 1. Geofence triggers only after Check-In 2. Shows Notification - "Geofence Entry Detected". 3. Pulse App Running in Background. | High | Pass | Pass | -
TC-GEO-012 | Verify Geofence record logging (Geofence Code/entry/exit/time/location) | Active Geofence | Geofence triggered at least once | 1. Open Geofence Record menu 2. Select Date 3. Tap Apply | Entry, Exit, Time, Location logs shown for selected date | Entry, Exit, Time, Location logs shown for selected date. | High | Pass | Pass | -
TC-GEO-013 | Verify map view options | Active Geofence | Geofence available | 1. Open Active Geofence 2. Tap View on App Map 3. Tap View on Google Map | Both maps display correct location | Both maps display correct location. | High | Pass | Pass | -
TC-GEO-014 | Verify Geofence does not trigger when Location/Internet is OFF | Active Geofence | Location/Internet disabled | 1. Turn off Location/Internet 2. Go near Geofence area 3. Try Check-In | Geofence should not trigger. Error message: “Enable Location & Internet” | Geofence don't trigger without internet | High | Pass | Pass | -
TC-GEO-015 | Verify all dropdowns scroll correctly when keyboard is open | All dropdowns (Doctor, Chemist) | Logged in as MIO/SMIO | 1. Tap Doctor dropdown (keyboard opens automatically) 2. Try scrolling to select options at bottom 3. Repeat for Chemist dropdown | Dropdown scrolls properly and selection works | Dropdown scrolls properly and selection works | High | Pass | Pass | -
TC-GEO-016 | Verify Doctor/Chemist list visibility in Pending Geofence List | Geofence created with Doctors only / Chemists only | Geofence submitted by MIO/SMIO, in Pending list | 1. Submit Geofence with only Doctors selected 2. Open Pending list 3. Check if Doctors are visible 4. Repeat with only Chemists selected | Submitted Doctors/Chemists should be visible in Pending list | Only list of Doctors showing; if only Chemists selected, chemists list not showing | High | Fail | Pass | Fixed
TC-GEO-017 | Verify geofence notification does not trigger without check-in | Location: ON Internet: ON Check-In: NO | User logged in, not checked in | 1. Ensure user is logged in but does not perform check-in 2. Visit assigned geofence location | Geofence should not trigger unless check-in is completed first | Geofence notification triggered even without check-in | High | Fail | Fail | Not Fixed Yet
TC-GEO-018 | Verify indication of active geofences in Submarket list | Any Submarket | Logged in as MIO/SMIO | 1. Open Submarket list 2. Check if Submarket shows geofence status without entering 3. Enter Submarket and check for geofence | Submarket list should clearly indicate if active geofences exist without needing to enter | No indication visible; user has to enter to check | Medium | Fail | Pass | Fixed
Test Scenario ID: TS-MIO-006
Feature: Tour Plan
Sub-Feature: Create / Edit / Draft / Approval / Validation
Scope: Ensure MIO/SMIO users can create, edit, and submit tour plans with correct validations, multiple selections, draft functionality, and supervisor approval flow.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-TOUR-001 | Create valid plan with mandatory fields | Session: Morning Location: Head Quarter Sub-Market: LIPSHA | User logged in as MIO/SMIO | 1. Select Date 2. Click “+” 3. Select Session 4. Location 5. Submit | Plan saved to pending list | Plan saved | High | Pass | Pass | -
TC-TOUR-002 | Submit without mandatory fields | Session: Evening Location: Outstation Miscellaneous: Meeting/Training/Half-day Leave/Full Day Leave | User logged in as MIO/SMIO | Click “+” → Leave Session & Location blank → Submit | Error shown, plan not saved | Error shown | High | Pass | Pass | -
TC-TOUR-003 | Multiple Submarket selection | Session: Morning, Location: HQ Miscellaneous: Meeting Submarkets: MOHANGANJ , LIPSHA | User logged in as MIO/SMIO | Select Session & Location → Add multiple Submarkets → Submit | Tour Plan saved with multiple Submarkets | Tour Plan saved | High | Pass | Pass | -
TC-TOUR-004 | Multiple Miscellaneous selection | Session: Morning, Location: HQ, Misc: Meeting + Half Day Leave | User logged in as MIO/SMIO | Select Session & Location → Add multiple Misc options → Submit | Should accept one Miscellaneous option | Only one Miscellaneous option is selected | High | Pass | Pass | -
TC-TOUR-005 | Save plan as Draft | Session: Evening, Location: HQ | User logged in as MIO/SMIO | Select Session & Location → Click Draft | Plan stored in Drafts | Draft works & editable | High | Pass | Pass | -
TC-TOUR-006 | Edit plan before approval | Valid submitted plan | Plan in Pending state | Open Pending plan → Edit details → Save | Plan updated in Pending list | Editable till approval | High | Pass | Pass | -
TC-TOUR-007 | Duplicate plan for same day & session | 2nd Sep, Session: Morning twice | Same | Try to add plan for same date & session twice | Error/duplicate blocked | Duplicate blocked | High | Pass | Pass | -
TC-TOUR-008 | Leave plan without Session/Location | Miscellaneous: Meeting Training Half-day Leave Full Day Leave | User logged in as MIO/SMIO | 1. Click “+” 2. Select Miscellaneous option (Meeting/Training/Half/Full Leave) 3. Do not select Session & Location 4. Submit | New Plan Created | Requires Session & Location to submit tour plan even for Leave | Medium | Fail | Pass | Updated in V2.2.0 → Can now submit Leave plan with Session - None & Location - Others
TC-TOUR-009 | Verify plan list shows correct month after plan creation | Create Plan For September | User logged in as MIO/SMIO | 1. Create a plan for September 2. Check plan list | Plan should appear under September | Plan appears under October | High | Fail | Fail | Not Fixed Yet
Test Scenario ID: TS-MIO-007
Feature: Order Management
Sub-Feature: Create / Edit / Draft / Submission / History
Scope: Verify that MIO/SMIO users can create, edit, draft, and submit orders correctly, with proper validations, automatic/manual delivery date handling, and order history tracking.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-ORD-001 | Create new order with valid details | Chemist: MAA PHARMACY Select Date Payment: Cash Product: SERGEL Qty 10 | Logged in as MIO/SMIO | 1. Select chemist 2. Select delivery date 3. Choose payment method - Cash or Card 4. Add product 5. Submit | Order submitted successfully | New Order submitted successfully | High | Pass | Pass | -
TC-ORD-002 | Verify automatic delivery date setting | Chemist: MAA PHARMACY Time < 2 PM / > 2 PM | Logged in | 1. Select chemist before 2 PM → Check delivery date 2. Select after 2 PM → Check delivery date | Before 2 PM → today After 2 PM → tomorrow | Delivery date set correctly based on time: today before 2 PM, tomorrow after 2 PM | High | Pass | Pass | -
TC-ORD-003 | Change delivery date manually | Chemist: MAA PHARMACY Custom date | Logged in | Select chemist → Change delivery date | Delivery date updated | Delivery date updated successfully to selected custom date | High | Pass | Pass | -
TC-ORD-004 | Verify product selection mandatory | None selected | Logged in | 1. Go to product screen → Do not select any product 2. Try Submit | System prevents submission, shows error | Submission blocked, error message displayed: “Select at least one product” | High | Pass | Pass | -
TC-ORD-005 | Delete product before submission | Product: SERGEL | Logged in | 1. Select product → Delete → Submit | Submission blocked if no product left | Cannot submit order after deleting all products | High | Pass | Pass | -
TC-ORD-006 | Draft order with products | Product: SERGEL | Logged in | 1. Select product → Draft | Draft saved, editable later | Draft saved successfully and can be edited later | High | Pass | Pass | -
TC-ORD-007 | Submit order after selecting products | Product: SERGEL | Logged in | 1. Select product → Submit | Order submitted, cannot edit | Order submitted successfully; cannot edit after submission. | High | Pass | Pass | -
TC-ORD-008 | Edit drafted order | Drafted order exists | Logged in | 1. Open draft → Edit product/quantity → Save | Draft updated successfully | Draft edited successfully; changes reflected in draft | High | Pass | Pass | -
TC-ORD-009 | Verify order history | Any orders exist | Logged in | 1. Go to Sales History → Check orders | Orders displayed with correct details | Orders displayed correctly with product, quantity, payment, and date details | High | Pass | Pass | -
Test Scenario ID: TS-MIO-008
Feature: Attendance / Check-In / Check-Out
Sub-Feature: Daily Attendance Tracking / Notifications / Location-based triggers
Scope: Ensure MIO/SMIO users can check in/out correctly with location & internet dependency, receive notifications, trigger dependent modules (attendance, geofence), and view history.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks
TC-CHK-001 | Check-in triggers only when Internet & Location are ON | Internet: ON, Location: ON | App installed, user logged in, check-out pending | 1. Open App 2. Click Green Check-In button 3. Allow Background Location permission | Check-In successful, button turns Red for Check-Out, dependent functions like attendance and geofence triggered, notification sent | Check-In works; button turns Red; attendance & geofence notifications triggered | High | Pass | Pass | -
TC-CHK-002 | Check-in requires background location permission | Internet & Location ON | App installed, user logged in | 1. Click Green Check-In button 2. Deny permission first 3. Click again and allow permission | App prompts for permission; check-in triggers after granting permission | Permission requested as expected; check-in successful after granting permission | High | Pass | Pass | -
TC-CHK-003 | Attendance & Geofence triggered upon check-in | Valid Check-In | User checked in | 1. Perform check-in 2. Observe notifications for attendance & geofence | Notifications received correctly; dependent modules updated | Attendance and geofence notifications received; all dependent functions triggered | High | Pass | Pass | -
TC-CHK-004 | Daily push notifications for check-in/check-out | Date: Today | App installed, user logged in | 1. Observe notification before 9 AM for check-in 2. Observe notification before 12 AM for check-out | Notifications appear correctly as per schedule | Notifications appeared at correct times during testing | High | Pass | Pass | -
TC-CHK-005 | Click Red Check-Out button after check-in | User checked in | User checked in | 1. Click Red Check-Out button 2. Grant background location access if prompted | Check-Out successful; button turns Green for next check-in | Check-Out works; button turns Green after granting permission | High | Pass | Pass | -
TC-CHK-006 | Check-in / Check-out history shows correct location & time | Valid Check-In/Check-Out | User checked in & checked out | 1. Open Left Sidebar → Check History | History shows correct location, check-in & check-out time for the day | History displays correct check-in/check-out time and location | High | Pass | Pass | -
TC-CHK-007 | Attempt check-in without Internet | Internet OFF, Location ON | User logged in | 1. Click Check-In button | App prevents check-in; error message shown | App blocked check-in; shows “Enable Internet” message | High | Pass | Pass | -
TC-CHK-008 | Attempt check-in without Location | Internet ON, Location OFF | User logged in | 1. Click Check-In button | App prevents check-in; error message shown | App blocked check-in; shows “Enable Location” message | High | Pass | Pass | -
TC-CHK-009 | Verify if app auto checks out after 12 AM if user forgets | User checked in previous day | User not checked out before 12 AM | 1. Keep app open or backgrounded past 12 AM 2.Observe auto check-out | App should automatically check out user; new check-in enabled next day | Auto check-out does not happen; check-out time in history shows N/A, but button turns green for next day check-in | High | Pass | Pass | -
TC-CHK-010 | Verify app prevents multiple check-ins without check-out | User already checked in | User checked in | 1. Click Check-In button again | App blocks second check-in; shows message “Already checked in” | App blocked second check-in as expected | High | Pass | Pass | -
TC-CHK-011 | Verify push notification reminders if user forgets check-out | User checked in | User not checked out | 1. Observe notification after 12 AM reminding check-out | Reminder notification appears to prompt user | Notification observed reminding user to check out | High | Pass | Pass | -
TC-CHK-012 | Verify user cannot check in twice on the same day | User already checked in today | User checked in today | 1. Attempt to click Check-In button again on same day | App prevents second check-in; shows message “Already checked in today” | App blocks second check-in with correct message | High | Pass | Pass | -
Test Scenario ID: TS-MIO-009
Feature: Notifications
Sub-Feature: Incoming Notifications & Handling
Scope: Ensure that all system notifications are received correctly, displayed properly, and navigate to the correct screens with accurate timing.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Previous Version (v2.1.5) | Status in Latest Version (v2.2.0) | Remarks / Version Notes
TC-NOTI-001 | Verify that all notification types (approval, geofence, check-in/out, etc.) are received | Normal usage | App installed, user logged in | 1. Perform actions that trigger notifications (approval, geofence, attendance) 2. Verify notifications are received | All notification types are received promptly | All notifications received as expected. | High | Pass | Pass | -
TC-NOTI-002 | Verify clicking on notification navigates to notification screen | Valid notifications present | User logged in | 1. Tap on a received notification 2. Observe navigation | App opens notification screen showing relevant details | Navigates correctly, but Today’s notifications list shows empty even though notifications exist. | Medium | Fail (intermittent) | Pass | Today’s notifications not always visible because it's not real time updating.
TC-NOTI-003 | Verify timing of Check-In/Check-Out notifications | Attendance actions performed | User has performed check-in and check-out | 1. Check-in at start of day 2. Check-out at proper time 3. Monitor notifications | Notification timing should match actual check-in/out times and not trigger incorrectly | Received wrong check-out notification at 12:36am despite having checked out at 5:57pm. | High | Fail | Fail | Incorrect notification timing for check-out