## Sheet1
3 Months Learning Roadmap - JavaScript & QA Tracking
Name: Jakia Rahman
Role: Intern (MIS) - Software Quality Assurance
Duration: 01-Sep-2025 to 30-Nov-2025
Phase | Task | Task Description | Tools | Start Date | End Date | Status
Phase 1 – JS Learning & Test Case Setup | JavaScript Tutorial | Complete a full JavaScript tutorial playlist | https://www.youtube.com/playlist?list=PLgH5QX0i9K3qzryglMjcyEktz4q7ySunX | 2025-09-01 | 2025-09-22 | Ongoing
| W3Schools JS Quiz | Take W3Schools JS quiz/test to assess learning | W3Schools | 2025-09-08 | 2025-09-11 | Ongoing
| JS Practice | Develop sign-up page with JS validation | VS Code / JS | 2025-09-08 | 2025-09-11 | Completed
| JS Practice | Develop tabular list view with JS | VS Code / JS | 2025-09-08 | 2025-09-11 | Completed
| JS Practice | Develop sample array/list JS functionality | VS Code / JS | 2025-09-08 | 2025-09-11 | Completed
| Personal Test Case Format | Finalize your own test case template/format | Excel | 2025-09-04 | 2025-09-09 | Completed
| Testing Criteria – Manual & Automation | Define manual & automation testing criteria | Excel | 2025-09-04 | 2025-09-09 | Completed
Phase 2 – Automation Testing | API Automation Testing | Learn and practice API testing with Postman | Postman | 2025-09-23 | 2025-10-05 | Started
Phase 3 – Selenium Automation | Selenium Automation | Automate websites using Selenium | Selenium, VS Code | 2025-10-06 | 2025-10-15 | Not Started
Phase 4 – Selenium Automation | Playwright Automation | Automation testing with playwright | Playwright | 2025-10-16 | 2025-10-25 | Not Started
Phase 5 – Load Testing k6 + Grafana | Load Testing with k6 | Learn and execute web app load tests | k6, Grafana | 2025-10-26 | 2025-11-06 | Not Started
Phase 6 – Load Testing Jmeter | Load Testing with JMeter | Build and execute load tests | Jmeter | 2025-11-09 | 2025-11-20 | Not Started
Phase 7 – GitHub Tracking & Wrap-up | Continuous GitHub Updates | Track all progress, update tasks, and maintain portfolio throughout internship | GitHub | 2025-09-01 | 2025-11-30 | Ongoing