## Sheet1
Ongoing Tasks Name: Jakia Rahman - Intern (MIS)
Task No | Task Description | Start Date | End Date | Status | Assigned By
1 | Practicing JavaScript (next important topics: event listeners, destructuring, callback, async/await, promise, array methods, etc.) | 2025-09-11 | 2025-09-22 | Ongoing | Md. Ashraful Maruf Anik
2 | Completed Phase 1 tasks | 2025-09-03 | 2025-09-11 | Completed | Md. Ashraful Maruf Anik
3 | Testing HPL HR (web and mobile app) | 2025-09-13 | 2025-09-14 | Ongoing | Md. Khaled Imam
4 | Gathering knowledge about tools and technologies for new project | 2025-09-09 | 2025-09-14 | Ongoing | Md. Najim Uddin
5 | Learning about authentication, authorization, JWT, Basic Auth, OAuth2 | 2025-09-11 | 2025-09-22 | Ongoing | Md. Ashraful Maruf Anik
6 | Request Healthcare Chemicals Quality Database | 2025-09-14 | 2025-09-15 | Pending for Sunday | Md. Najim Uddin
7 | Request Pulse app demo API to test in Postman | 2025-09-23 | TBA | Pending for Sunday | Md. Ashraful Maruf Anik
8 | SAP Testing | 2025-09-18 | TBA | Ongoing | Md. Khaled Imam
9 | HCL Landing Page Devlopment | 2025-09-18 | 2025-10-15 | Ongoing | Engr. S.M. Shahiduzzaman