## MIO-SMIO
Software Test – Pulse App LK
Test Case Execution Document
Test Run Information:
|  |  | Tester Name: Jakia Rahman Date of Test: 14 - 09 - 2025 | Application Name : Pulse App - LK (Sri Lanka Version) Application Version: v1.0.0 Device: Android Android Version: LK
Test Execution Summary: | Result
Total Test Scenarios Executed: | 4
Total Test Cases Executed: | 31
Passed: | 18
Failed: | 8
Yet to be Tested: | 5
Test Scenario ID: TS-001
Feature: Doctor Management
Sub-Feature: Add, Edit, Inactivate, Transfer, Search
Scope: To validate core doctor lifecycle operations (add, edit, inactivate, transfer, search) with approval workflow.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Current Version | Remarks
TC-DOC-001 | Add a new doctor | 1. Basic Info 2. Medical Info 3. Target Brands 4. Image 5. Summary | User logged in and on Doctor Management Screen | 1. Click "Add Doctor" 2. Fill data 3. Click Save | Doctor is saved and visible in list | Doctor could not be added, showing "Something went wrong" | High | Fail | -
TC-DOC-002 | Mark doctor as inactive | 1. Dr. Samantha | Doctor exists and active | 1. Select doctor 2. Click "Inactive" 3. Confirm | Doctor status changes to Inactive and not selectable in DCR/Tour Plan | Doctor status changed to Inactive, gone from active doctor list, not selectable in DCR/Tour Plan | High | Pass | Works as expected.
TC-DOC-003 | Edit doctor details | 1. Change any details | Doctor exists and active | 1. Select doctor 2. Click Edit 3. Modify contact 4. Save | Updated details visible in submitted doctor list. | Doctor list updated; edited doctor moved to "Pending Doctor List" for supervisor approval | High | Pass | Works as expected.
TC-DOC-004 | Transfer doctor to another submarket | 1. Doctor 2. Submarket | Doctor exists and active | 1. Select doctor 2. Click "Transfer" 3. Select new submarket 4. Save | Doctor assigned to new submarket; reflected in relevant modules | Doctor list refreshed, doctor shifted to "Pending Doctor List" for approval | High | Pass | Works as expected.
TC-DOC-005 | Active Doctor List Shows All Doctors Together/ Sub- Market Wise Filtering | Active Doctor List of All Sub-Market | Logged in as MR | Open Active Doctors list → Refresh | 1. All doctors of MR’s submarket appear 2. Clicking respective Submarket shows only their doctors 3. Refresh works correctly | 1. All doctors initially shown 2. Click another Submarket 3. Correct filtered doctors shown 4. Refresh still shows all doctors again of all submarkets even though filter is applied | Medium | Fail | Refresh still shows all doctors again of all submarkets even though filter is applied
Test Scenario ID: TS-002
Feature: Geofence
Sub-Feature: Create / Edit / Trigger / Record / Map View
Scope: Verify that MR's can create, edit, trigger, and view geofences with proper validations, notifications, and record/map functionality.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Current Version | Remarks
TC-GEO-001 | Verify submitting Geofence without a name | Geofence Name = Blank | Logged in as MR Submarket exists | 1. Open Submarket module 2. Select Submarket 3. Click “Geofence Points of This Submarket” 4. Click “+” Icon 5. Leave Geofence Name blank 6. Select Doctor 7. Tap Set Location | Error shown: “Please Enter Geofence Name” | Error shown: “Please Enter Geofence Name” | High | Pass | -
TC-GEO-002 | Verify submitting Geofence without selecting Doctor | Geofence Name = Test Doctor = None | Logged in as MR Submarket exists | 1. Enter Geofence Name 2. Do not select Doctor 3. Tap Set Location | Error shown: “Please Select a Doctor” | Error shown: “Please Select a Doctor” | High | Pass | -
TC-GEO-003 | Verify submitting Geofence selecting multiple Doctor | Geofence Name = Test Doctor = Multiple | Logged in as MR Submarket exists | 1. Enter Geofence Name 2. Select multiple Doctors 3. Tap Set Location | Geofence created successfully with multiple Doctors | Geofence created successfully with multiple Doctors | High | Pass | -
TC-GEO-004 | Verify Pending → Approval workflow | Submitted Geofence | Geofence submitted and in Pending List | 1. Submit Geofence 2. Check Pending list 3. Supervisor approves | Geofence disappears from Pending list, moves to Active list | Shows on Active List after Supervisors Approval | High | Yet to be Tested | -
TC-GEO-005 | Verify Geofence triggers only after Check-In | Active Geofence, location mapped | MR inside Geofence radius | 1. Go near Geofence area 2. Without Check-In → verify 3. With Check-In → verify | Geofence triggers only after Check-In | 1. Geofence triggers only after Check-In 2. Shows Notification - "Geofence Entry Detected". 3. Pulse App Running in Background. | High | Yet to be Tested | -
TC-GEO-006 | Verify Geofence record logging (Geofence Code/entry/exit/time/location) | Active Geofence | Geofence triggered at least once | 1. Open Geofence Record menu 2. Select Date 3. Tap Apply | Entry, Exit, Time, Location logs shown for selected date | Entry, Exit, Time, Location logs shown for selected date. | High | Yet to be Tested | -
TC-GEO-007 | Verify map view options | Active Geofence | Geofence available | 1. Open Active Geofence 2. Tap View on App Map 3. Tap View on Google Map | Both maps display correct location | Both maps display correct location. | High | Yet to be Tested | -
TC-GEO-008 | Verify Geofence does not trigger when Location/Internet is OFF | Active Geofence | Location/Internet disabled | 1. Turn off Location/Internet 2. Go near Geofence area 3. Try Check-In | Geofence should not trigger. Error message: “Enable Location & Internet” | Geofence don't trigger without internet | High | Yet to be Tested | -
TC-GEO-009 | Verify geofence notification does not trigger without check-in | Location: ON Internet: ON Check-In: NO | User logged in, not checked in | 1. Ensure user is logged in but does not perform check-in 2. Visit assigned geofence location | Geofence should not trigger unless check-in is completed first | Geofence notification triggered even without check-in | High | Pass | -
TC-GEO-010 | Verify indication of active geofences in Submarket list | Submarkets assigned with geofence | MR logged in, geofence created | 1. Navigate to Submarkets list 2. Check geofence tags/status 3. Compare with active geofence list | Submarkets with active geofence should show correct “Geofence Covered” tag | Submarkets show tag “Geofence Covered” but no active geofence is visible on respective submarkets | High | Fail | -
Test Scenario ID: TS-003
Feature: Tour Plan
Sub-Feature: Create / Edit
Scope: Verify that users can create, edit, and submit Tour Plans with proper session, Submarket, and exception handling until supervisor approval.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Current Version | Remarks
TC-TP-001 | Verify successful Tour Plan creation | Session: Morning Location: Head Quarter Sub-Market: MATARA | MR logged in | 1. Select Date 2. Click “+” 3. Select Session 4. Location 5. Submit | Plan saved to Pending List | New Tour Plan saved | High | Pass
TC-TP-002 | Verify Tour Plan is editable until Supervisor approval | Tour Plans in Pending List | MR logged in, Tour Plan not yet approved | 1. Open created Tour Plan 2. Edit details (Submarket, Session) 3. Save changes | Tour Plan updated successfully and remains in Pending until approval | Tour Plan updated successfully and remains in Pending until approval | High | Pass
TC-TP-003 | Verify Tour Plan cannot be edited after Supervisor approval | Approved Tour Plan exists | Tour Plan approved by Supervisor | 1. Open approved Tour Plan 2. Try to edit details | Edit option disabled | No edit option | High | Pass
TC-TP-004 | Verify changing session allows editing and resubmission | Tour Plans in Pending List | MR logged in, Tour Plan not yet approved | 1. Open Tour Plan 2. Change session (Morning → Evening) 3. Save changes 4. Submit Tour Plan | Tour Plan updated with new exceptional session and submitted for approval | Changing from regular session to exceptional session does not allow resubmission Error shown: "An error occurred while tour plan entry" | High | Fail
TC-TP-005 | Verify adding Submarket in Optional Meetings allows resubmission | Tour Plans in Pending List | MR logged in | 1. Open Tour Plan 2. Change session (Morning → Meeting) 3. Add Submarket 4. Save changes 5. Submit Tour Plan | Tour Plan successfully submitted with Optional Meeting details | Error shown: "An error occurred while tour plan entry" | High | Fail
TC-TP-006 | Verify updating exception option in Tour Plan | Tour Plans in Pending List Session - None, Location - Other, Exception - Training | MR logged in | 1. Open Tour Plan 2. Change Exception (Half-day leave → Meeting) 3. Save changes 4. Submit Tour Plan | Tour Plan successfully submitted with Optional Meeting update | Shows "Tour Plan Submitted Successfully" but Tour Plan list does not update with new changes | High | Fail | Happens only when choosing any of the exception options; other sessions work correctly
TC-TP-007 | Verify duplicate Submarket selection in Optional Meetings is not allowed | Tour Plan with one Submarket already added | MR logged in | 1. Open Tour Plan 2. Try adding the same Submarket again under Optional Meetings | System shows error “Submarket already selected” | System shows error “Submarket already selected” | High | Pass
TC-TP-008 | Verify exception tags change accordingly upon edit | Tour Plan created | MR logged in | 1. Open Tour Plan 2. Change Exception (Half-day leave → Regular Session), Change Submarket 3. Save changes 4. Submit Tour Plan | Exception tags should update according to changes | Exception tags do not change after edit; old tags remain | High | Fail | System not updating exception tags upon edit
TC-TP-009 | Verify Tour Plan submission without mandatory fields (Submarket/Session) | Missing data | MR logged in | 1. Create Tour Plan without selecting Submarket 2. Tap Submit | Error message displayed "Please Select Submarket" | Error message displayed "Please Select Submarket" | High | Pass
TC-TP-010 | Verify submitted Tour Plan moves to Pending List for approval | Complete Tour Plan filled | MR logged in | 1. Create Tour Plan with valid Submarket, Session 2. Tap Submit 3. Check Pending List | Tour Plan appears in Pending List | Tour Plan appears in Pending List | High | Pass
TC-TP-011 | Verify Tour Plan calendar view displays all sessions correctly | Tour Plan created with Morning & Evening sessions | MIO/SMIO logged in | 1. Open Tour Plan calendar view 2. Navigate through dates | All plans are displayed correctly on calendar | All plans are displayed correctly on calendar | Medium | Pass
TC-TP-012 | Verify Tour Plan can be created for future dates | Valid future date selected | MR logged in | 1. Create Tour Plan with date 2. Submit | Tour Plan successfully created and submitted | Tour Plan successfully created and submitted | Medium | Pass
Test Scenario ID: TS-004
Feature: Doctor Call Management - DCR
Sub-Feature: Create / Edit / Draft / Submit
Scope: Verify that users can create, edit, save as draft, and submit Doctor Call Records (DCR) with correct draft handling and submission workflow.
TC ID | Test Case Description | Test Data | Precondition | Steps | Expected Result | Actual Result | Severity | Status in Current Version | Remarks
TC-DCR-001 | Verify successful DCR creation | Doctor: Dr. Silva Location: HQ Shift: Morning | MR logged in | 1. Navigate to DCR module 2. Click “+” to create DCR 3. Select Doctor, Submarket, Session 4. Add notes/remarks 5. Save and Submit | DCR created successfully and visible in Submitted List | DCR created successfully and visible in Submitted List | High | Pass
TC-DCR-002 | Verify saving DCR as Draft | Doctor: Dr. Silva Location: HQ Shift: Morning | MR logged in | 1. Create DCR 2. Click “Draft” | DCR saved in Draft List | DCR saved in Draft List | High | Pass
TC-DCR-003 | Verify editing a DCR from Draft removes it from Draft List after edit | DCR exists in Draft List | MR logged in | 1. Open DCR from Draft List 2. Edit any details 3. Save changes | Edited DCR removed from Draft List and appears in Submitted List only | Edited DCR still shows in Draft List and Submitted List | High | Fail | Issue: DCR remains in Draft List after editing; system bug
TC-DCR-004 | Verify submitting a DCR directly from Draft List without editing | DCR exists in Draft List | MR logged in | 1. Open DCR from Draft List 2. Click Submit without editing | DCR removed from Draft List and appears in Submitted List | DCR disappears from Draft List and showing in submitted list | High | Pass